## Sheet1
This table provides the framework for a timeline of past, ongoing, and future actions and associated outcomes the LIT identified as necessary to develop the Prineville LIT Strategic Action Plan.
Timeline to complete | Proposed subgroup to develop this step | Action | Outcomes | Notes
Sept. 2020 | LIT | Establish criteria that will prioritize how the LIT addresses threats - High priority threat - Need more information to address threat - Need more resources to address threat - Low priority threat | • create a shared vision for what the LIT can do
Oct. 2020 | Crooked River WMA, BLM, ODFW, SageCon, USFS, USFWS, | Finalize the threats list | • the list consists of 16 threats to sage-grouse habitat and populiations, and threats that result from development impacts • finalizing a list of threats for the LIT to focus on will allow the LIT, 1. develop long-term goals and objectives 2. monitor effectiveness of actions and apply adaptive management
|  | Prioritze threats based on criteria set in Sept. - partners presented assessments for each threat to show distribution and severity with Prineville area | LIT participants placed threats in each of the four categories (two threats placed in two prioritization categories). • 5 threats set as high priority • 5 threats need more information • 3 threats need more resources • 5 threats as low priority
Nov. 2020 | LIT | Develop an outline for the Prineville LIT Strategic Action Plan; identify specific actions necessary to create this plan (outlined as actions below) | Prineville LIT to use the Baker LIT plan as a template, 1. establish action areas to compartmentalize into manageable planning zones 2. identify relevant conservation efforts that have already occurred in each action area. 3. identify threats remaining in each action area 4. direct future actions to address threats in each action area
Jan. 2021 | ODFW, BLM, USFS, SWCDs, NRCS, ECAS | Modify 2012 Action Areas - use current data with active leks - create movement/dispersal corridors between active lek areas | • Address current habitat and population conditions • Prioritize project implementation efforts | Emily Weider and Julie Unfried coordinating this sub-group which will meet and advance these actions in time to present to the larger LIT at the January meeitng
Identify threats in each action area then bring that information to the larger group to discuss - identify competing objectives at the same time (i.e., other species and demands on the landscape)
Pending CED data | SageCon, ODFW, BLM, USFS, DSL, NRCS, SWCDs | Compile relevant informaiton about conservation efforts that have already occurred in each action area - Compile data in the CED - Communicate local coordination efforts to the LIT | • Use the CED (focus on priority threats) to tally conservation actions. Map and discuss. • Assess effectiveness of efforts that have been implemented (use lek data - conduct analysis of lek counts in relation to completed conservation actions • Use information to prioritize efforts moving forward | • Megan Creutzburg actively coordinating with developers of the CED to get OR data entered asap. Should be updated before January meeting • Waiting on CED will save partners from reporting project work twice (i.e., to the CED and to the LIT).
|  | Direct future actions to address threats in each action area - develop goals and objectives - identify other information needed to continue work into the future - e.g., NEPA | • goals and objectives will provide an inventory of opportunities for the LIT address • identify existing barriers to implementation
|  | Develop Prineville LIT Strategic Action Plan - compile information previously compiled (actions outlined above) into the plan | • demonstrate coordinated approach to conservation within the Prineville LIT area • highly competative for grant funding | • determine when to incorporate development of long-term monitoring protocols to assess effectiveness/apply adaptive management
|  | Identify long-term funding opportunities | • implement cross-boundary actions outlined in the Prineville LIT Strategic Action Plan